## Cover Page
<Project Name>
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Keval
| Role | Genc
Signature
| Date | 2019-12-01
Project ID: Car Servicing | HYD19IJ003/148 |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Online Blood Bank System
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Req_1 | Task_1 | Home Page:Home page should have some information why Blood donation is required and options for login and registration | Keval | 0.5 | 0.3 | 0.1 | 0.1 |  |  |  | Completed
Req_2 | Task_1 | User Registration. Create User Registration form/Create Authentication-Service for validating registration details entered by the user using Spring. |  | 1 | 0.4 | 0.6 | 0.1 |  |  |  | Completed
Req_3 | Task_1 | Validating Login and Registration details entered by the user with Postman. |  | 0.5 |  | 0.3 | 0.3 |  |  |  | Completed
| Task_2 | Create angular files of login and registration and integrate with Spring files. |  | 0.5 |  |  | 0.5 |  |  |  | Completed
Req_4 | Task_1 | Blood Availability:Database EER diagram and schema is generated,Then Create Blood Availability Entity Classes |  | 0.3 |  |  | 0.3 |  |  |  | Completed
| Task_2 | Create Blood Availability form/Create the details to validate the available details entered by the user |  | 0.2 |  |  | 0.1 | 0.2 |  |  | Completed
| Task_3 | Create required Repository,Service,Controller Classes and validate with database using postman. |  | 0.2 |  |  |  | 0.2 | 0.1 |  | Completed
| Task_4 | Create a Blood Availability form to perform data from Springto Database and database to Angular/(Validation) |  | 0.3 |  |  |  | 0.3 | 0.1 |  | Completed
Req_5 | Task_1 | BloodRequirementPosting:Create Blood Required form for posting the details if blood is not available in database.Create the details to validate the available details entered by the user and display error for the fields not matching. |  | 0.3 |  |  |  | 0.3 | 0.1 |  | Completed
| Task_2 | If Blood is not Available route the page of Blood Available to available-status form Where it requests us to go to blood request Form.If blood is available it gives the Details of the person containing that blood Group. |  | 0.2 |  |  |  | 0.1 |  | 0.1 | Completed
| Task_3 | Create a UI form to perform data from spring to Database and database to angular. |  | 0.2 |  |  |  |  | 0.2 |  | Completed
Req_6 | Task_1 | Blood Donation:Create Blood Donation form for posting the details/Create the details to validate the available details entered by the user and display error for the fields not matching |  | 0.3 |  |  |  |  | 0.3 |  | Completed
| Task_2 | Ability of the system to store the details of blood donated by a user. |  | 0.2 |  |  |  |  | 0.15 | 0.05 | Completed
Req_7 | Task_1 | Experience-Sharing:Ability of the system to capture the experience of a blood donor and display on the home page. |  | 0.3 |  |  |  |  | 0.2 | 0.1 | Completed
| Task_2 | Create a database to post the details |  | 0.4 | [5 empty] | 0.4 | Completed
Req_8 | Task_1 | Create FAQ page for knowing about the Donating of blood/the user can also raise a query so raise a query page. |  | 0.2 | [5 empty] | 0.2 | Completed
| Task_2 | Create a database table to Store User details he can be view in home page. |  | 0.4 | [5 empty] | 0.4 | Completed
|  | Total |  | 6 | 0.7 | 1 | 1.4 | 1.1 | 1.15 | 1.25
Sprint Goal
Some sprint goal

## Sprint 2
Sprint Backlog <Project name> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A